## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Understanding project scope, security goals, and defining responsibilities for the Scanning Engine layer | MUST HAVE | No Dependency | Nithish Kumar | 3 - Completed
S1 | S1 | US-002 | Setting up development environment including Python, Nmap, FastAPI, and project structure | MUST HAVE | US-001 | Nithish Kumar | 3 - Completed
S2 | S2 | US-003 | Designing automated target input handling and validation for scanning engine | MUST HAVE | US-002 | Nithish Kumar | 3 - Completed
S2 | S2 | US-004 | Implementing Nmap-based port scanning and service discovery | MUST HAVE | US-003 | Nithish Kumar | 3 - Completed
S2 | S2 | US-005 | Integrating service version detection for accurate vulnerability mapping | MUST HAVE | US-004 | Nithish Kumar | 3 - Completed
S3 | S3 | US-006 | Adding vulnerability detection using Nmap vulnerability scripts | MUST HAVE | US-005 | Nithish Kumar | 3 - Completed
S3 | S3 | US-007 | Parsing raw Nmap XML output into structured data format | SHOULD HAVE | US-006 | Nithish Kumar | 3 - Completed
S3 | S3 | US-008 | Normalizing scan output into consistent JSON schema for downstream layers | SHOULD HAVE | US-007 | Nithish Kumar | 3 - Completed
S4 | S4 | US-009 | Implementing scan-once, store-once architecture for reuse across APIs | SHOULD HAVE | US-008 | Nithish Kumar | 3 - Completed
S4 | S4 | US-010 | Exposing scanning engine output through FastAPI endpoints | MUST HAVE | US-009 | Nithish Kumar | 3 - Completed
S4 | S4 | US-011 | Designing dashboard-friendly aggregated scan summaries | SHOULD HAVE | US-010 | Nithish Kumar | 3 - Completed
S5 | S5 | US-012 | Optimizing scan commands to balance speed and vulnerability coverage | SHOULD HAVE | US-011 | Nithish Kumar | 3 - Completed
S5 | S5 | US-013 | Handling error cases, invalid targets, and scan failures gracefully | SHOULD HAVE | US-012 | Nithish Kumar | 3 - Completed
S6 | S6 | US-014 | Performing end-to-end validation of scan output across code, API, and demo | SHOULD HAVE | US-013 | Nithish Kumar | 3 - Completed
S6 | S6 | US-015 | Preparing research documentation for the Scanning Engine layer | MUST HAVE | All Layer-1 Tasks | Nithish Kumar | 2 - Completed
S6 | S6 | US-016 | Preparing developer documentation, PPT, and demo explanation for Scanning Engine | MUST HAVE | US-015 | Nithish Kumar | 2 - Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7